## Slide 1
Workflow – Best Ofs
Pre-IO
No IO
IO signed
Sales alerts editor to lead -- may request further details/ideas. Discuss scheduling w/Content.
Ad Ops | 
Content/Editorial | 
Product | 
Sales | 
Tech | 
Legend
Content for BST is sourced from what SB has already covered in the previous year; “Who is the thought leader”? Can’t know that until the BST is sold.

## Slide 2
Workflow – Best Ofs
Post-IO
IO signed
Sales alerts editor, Ad Ops
Editors/Sales confirm that set BST send date and pre-BST poll dates are okay
Editors write polls, send to Partner for review. Editor asks Partner for thought leader recs and any Partner content (letter from CEO, etc)
Ad ops sends specs to advertiser and schedules ads
Editors format BST in Alchemy
Editors mine content archives; continues to work with Partners on getting their resources (news items, calendar items, letter from CEO, etc)
Editors edit BSTs as soon as is feasible
Editor coordinates Partner review; 24 hrs required
Editors incorporate partner edits
2-3 days before send: Copy edit and promote in Alchemy
Ad ops inserts ads and tests ads; promotes to launch queue
Tech schedules launch for early A.M.
Editor communicates any special launch instructions to Ad Ops (e.g. timing of send)
8 weeks timeline
Editors run poll questions (x3)
Editors interview thought leader
Blog post interview must be formatted for Wordpress, copyedited, and scheduled to post the day BEFORE BST send

## Slide 3
Workflow – Special Report
Post-Delivery
BST publishes
Ad ops reporting
Alchemy reports clicks on ads
Alchemy reports clicks on polls